## UAT sign off Testcases
SR NO | Defect ID | SFDC ID/Devops id | HF version | Tester | Defect Description | Test cases | Expected | Status
1 | UAT5-24 | 220271 |  | Vrushali | After click on yes for "do you want to continue where you left" popup, save for later transaction data is not coming - issue with populating the data | Initiate single data entry and submit | User should able to Initiate single data entry and submit
[6 empty] | Initiate another single date entry by entering some data and click on bulk button | Iuser should able to nitiate another single date entry by entering some data and able to click on bulk button
[6 empty] | Click on save for later option from popup | User shoukd able to Click on save for later option from popup
[6 empty] | Again click on single button and click on yes for do you want to continue popup | User shoukd able to Again click on single button and click on yes for do you want to continue popup
[6 empty] | Check if correct entered data is getting displayed | correct entered data should get display.
2 | UAT5-88 | 249091 |  | Vrushali | Payment approval widget displaying blank, no data is getting displayed. | Log in with checker and check if user is able to see data in payment approval widget | User should able to Log in with checker and user is able to see data in payment approval widget
3 | UAT5-94 | 253918 |  | Gaurav | Enrichments are not being displayed on BDE preview page >>View Additional Info popup | Navigate to create payment page & select Batch | Batch txn creation page should be displayed. | Pass
[6 empty] | Save one payment and click on 'Next' button | Navigates to Preview page. | Pass
[6 empty] | Click on 3 dots of added payment & then click on 'View Additional Info'. | Instrument Details' popup window should be displayed. | Pass
[6 empty] | Verify that 'Enrichments' are being displayed correctly on Instrument details page | Enrichments should be displayed correctly on "Instrument Details" page | Pass
5 | UAT5-104 | 256767 |  | Pallavi
6 | UAT1-331 | 258948 |  | Pallavi | Error displaying at amount field in FCC while modifying txn
7 | UAT5-106 | 258938 |  | Gaurav | Total amount ' field should proper aligned in the batch payment grid
| UAT5-51 | 234710 |  | Pallavi | suspend and enable option is displayed for suspend beneficiary in the widget.
8 | UAT5-19 | 219893 |  | Pallavi | Beneficiary creation for multiple accounts is not working | Navigate to create beneficiary screen and enter bene code bene name and other details | Bene creation page will display and user will able to enter all details
[6 empty] | Save the first account and click on Add accounts to add more | User should able to add account
[6 empty] | Enter upto 10 accounts in same beneficiary and click on Next | User should able to add 10 accounts and click on 'Next' button
[6 empty] | On preview screen all 10 added beneficiary will display | All Bene accounts sholud display
[6 empty] | Click on Submit button, beneficiary successfully submtted screen will display | Bene should created successfully with 10 accounts.
| UAT5-46 | 233006 |  | Vrushali | Count of pending my approval tab is not correct
| UAT5-62 | 238104 |  | Vrushali | Actions buttons which should available after click on checkbox getting hide In pending my verification tab or pending my approval tab or pending send tab after performing any action
| UAT5-21 | 219906 |  | Gaurav | Navigation issue from widget to payment list.
| UAT4-98 | 214124 |  | Gaurav | In Payment status widget, if user clicked on see more then total 10 records displaying. After that if user clicked on any record and cancelled, then only 5 records are getting displayed with view more option